## Sheet1
Summary Information on Website
Part of the Councils Quality Assurance Reporting Procedure for the year under review is to publish summary information on its website under a heading PROCUREMENT/PROJECT PROGRESS of all procurements (capital and current) of Contracts in excess of €10m, relating to Projects in progress or completed (in the year under review). A new project may become a “project in progress” during the year under review if the procurement process is completed and a contract is signed. The Project below is identified in the Inventory list of Projects/Programmes contained in the Councils Quality Assurance Report for the year under review and the information provided below refers to that element of the Project were the procurement process was for a contract with a value in excess of €10m. The information provided is in accordance with the relevant guidelines and will remain on the Councils website until reported as completed.
Project Details
Year: | 2022
Parent Department: | Roads and Transportation
Name of Contracting Body: | Cavan County Council
Name of Project/Description: | N55 Corduff to South of Killydoon Realignment Scheme - Section B
Procurement Details
Advertisement Date: | 2022-06-03
Tender Advertised in: | etenders and OJEU
Awarded to: | Clare Civil Engineering Ltd
EU Contract Award Notice Date: | 02/02/2023 - Notice number oj 2023/S 027-077679
Contract Price: | 19807317.5
Progress
Start Date: | 21st December 2022 (Contract date) 30th January 2023 (Works start date)
Expected Date of Completion per Contract: | 18th December 2024 - projected substantial completion date
Spend in Year under Review: | 0
Cumulative Spend to End of Year: | 0
Projected Final Cost: | 19807317.5
Value of Contract Variations: | 0
Date of Completion: | Not completed
Outputs
Expected Output on Completion (E.G. XX kms of Road, No of units etc) | * 3.7 km of realigned National Secondary Road to a Type 2 single carriageway standard; * Realignment of 2 no. local side roads, construction of 5 no. side roads to link bypassed sections of the existing N55 and the construction of numerous direct accesses; * Three new over bridges across the River Erne; * Two new retaining walls * Public Lighting; * Traffic Calming works in bypassed Killydoon Village, * and all ancillary works
Output Achieved to date (E.G. X kms of Roads, No of Units etc) | As of year end 2022 the construction contract had not commenced
Notes:
o The requirement to publish relates specifically to procurement and not the project so where a project is reported at over €10m the interpretation here is that the project is examined and only the elements of that project that were the subject of a procurement process for a contract in excess of €10m needs to be reported. Therefore if a project with a total expenditure in excess of €10m is made up of procurements assigning more than one contractor and none of these contracts exceed the €10m threshold then there is no requirement to include them in the list for publication.
o Year = Year of review
o Parent Department = LA name